Mosquito and Vector Control Districts   
Program EIR Addendum

Project Schedule

| Work Product/Milestone | Due Date |
| --- | --- |
| Kickoff meeting with Ascent/Districts | March 11, 2024 |
| Ascent submits table templates for Districts input | April 12, 2024 |
| Districts submit completed tables | April 26, 2024 |
| 2nd Kickoff Meeting with Ascent/Bill Williams/Districts to discuss input | Early May 2024 |
| Ascent submits Admin Draft Description of program changes to districts | May 17, 2024 |
| Districts submit comments on Admin Draft Description | May 31, 2024 |
| Ascent submits Revised Draft Description of program changes to districts | June 14, 2024 |
| Ascent submits Admin Draft Ecological and Human Health Assessment Report and Admin Draft Alternatives Report | August 16, 2024 |
| Ascent submits Admin Draft Bio Resources Assessment | September 27, 2024 |
| Districts submit comments on Admin Draft technical reports | October 18, 2024 |
| Meeting with Ascent/Bill Williams/Districts to discuss Admin Draft technical reports | Late October 2024 |
| Ascent submits Revised Draft Ecological and Human Health Assessment Report and Revised Draft Alternatives Report | November 8, 2024 |
| Ascent submits Revised Draft Bio Resources Assessment | December 6, 2024 |
| Ascent submits Admin Draft checklist template with appended technical reports | January 17, 2025 |
| Districts submit comments on Admin Draft checklist template with appended technical reports | February 7, 2025 |
| Meeting with Ascent/Bill Williams/Districts to discuss Districts’ comments on Admin Draft checklist template | Mid-Feb 2025 |
| Ascent submits Revised Draft checklist template with appended technical reports | March 7, 2025 |
| Ascent submits CEQA Determination Memo | March 14, 2025 |
| Ascent submits Admin Draft Addendum (assumed CEQA document) | March 21, 2025 |
| Districts submit comments on Admin Draft Addendum | April 4, 2025 |
| Meeting with Ascent/Bill Williams/Districts to discuss Districts’ comments on Revised Draft Addendum | Early-Mid April 2025 |
| Ascent submits Final Addendum | April 30, 2025 |

Note: If Districts would like public review, additional schedule will be added